## Sprint Backlog
Task Name | Estimated Hours to use |  |  |  |  | Status | Total Hours Use
| Mon | Tues | Wed | Thus | Fri
Sprint 1
Design the user interface | 3 | 3 |  |  |  | Completed | 6
Code the user interface |  | 2 | 3 | 3 | 5 | Completed | 13
Code the login and register functions | 5 | 2 |  |  |  | Completed | 7
Create validation for login and register function |  |  | 3 | 3 | 2 | Completed | 8
Session Login |  | 1 |  |  |  | Completed | 1
Create Database | 1 |  |  |  |  | Completed | 1
36
Sprint 2
User Interface admin and student's contribution upload |  |  |  | 3 | 3 | Completed | 6
Admin register coordinator |  |  |  |  | 2 | Completed | 2
Upload images and document file type |  |  |  | 5 | 5 | Completed | 10
Designing diagram |  |  |  | 3 | 2 | Completed | 5
23
Sprint 3
Allow the coordinator to view contribution | 3 |  |  |  |  | Completed | 3
Create Burn Down Chart | 4 |  |  |  |  | Completed | 4
Creating Coursework task and brief explaining in excel |  | 2 |  |  |  | Completed | 2
Doing Research on coding dowload zip file and code the function | 8 | 5 |  |  | 8 | Completed | 21
Doing Research for Coding Chart and Coding the chart function |  | 5 | 3 |  |  | Completed | 8
38
Sprint 4
Coding for Dowload zip file function | 5 | 5 |  |  |  | Completed | 10
Coding for chart function | 5 |  | 5 |  |  | Completed | 10
Coding for Sending Email and notification function | 1 |  |  | 2 | 5 | Completed | 8
28
Sprint 5
Make some changes for the coding chart function | 5 |  |  |  |  | Completed | 5
Testing Whole System (if have problem, will try to solve) | 3 | 3 | 3 | 3 | 3 | Completed | 15
Starting Final Documantation | 2 | 2 | 2 | 2 | 2 | Completed | 10
25
[7 empty] | 135 | 350 (total hours can used)